## Plan
# | Description | Required Hours | Status
1 | Intro to mobile development technologies vs Xamarin | 2 | Done
2 | Environment installation and configuration with “hello world” project. | 2 | Done
3 | XAML vs Code. | 4 | Done
4 | Xamarin Forms Pages. | 2 | Done
5 | Navigation. | 2
6 | Xamarin Forms Layout. | 6
7 | Xamarin Forms Views. | 6
8 | Localization and Multi-Language. | 2
9 | Styles and Themes. | 2
10 | Binding Values and Commands. | 2
11 | Into to Animations | 4
12 | MVVM pattern. | 2
13 | Other (On Platform, compilers ...etc.). | 4
14 | Intro to Xamarin.Android and Xamarin.iOS | 4
15 | Custom Renders. | 2
16 | Automated Testing (Unit Test and UI Test). | 2
17 | Deployment to Google Play and App Store. | 4
18 | Best practice for full project including iOS, Android, back-end API and DB. | 8
| Total | 60

## timesheet
# | Date | Description
1 | 2019-02-21 | Intro to mobile development technologies vs Xamarin
2 | 2019-02-26 | Environment installation and configuration with “hello world” project.
3 | 2019-02-27 | XAML vs Code and Xamarin Forms Pages.